## v1
Mega Process | MPO | PDC Program | Phase | Plan | Completions | % to Plan | % to Plan | Check
ED Maintenance | Ron Richardson | COE Capital | Total in WP | 0 | 1034 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Rebaseline | 0 | 1051 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Execute | 838 | 971 | 1.1587 | 1.1587 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Schedule | 1051 | 943 | 0.8972 | 0.8972 | TRUE
ED Maintenance | Ron Richardson | COE Capital | EOY Forecast | 0 | 1034 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Design | 1051 | 984 | 0.9363 | 0.9363 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Annual Target | 1051 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Dependencies | 1051 | 897 | 0.8535 | 0.8535 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Initiation | 1051 | 997 | 0.9486 | 0.9486 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Initiation | 1106 | 1241 | 1.1221 | 1.1221 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Execute | 884 | 1139 | 1.2885 | 1.2885 | TRUE
ED Maintenance | Ron Richardson | COE Expense | EOY Forecast | 0 | 1243 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Total in WP | 0 | 1243 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Schedule | 1171 | 1076 | 0.9189 | 0.9189 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Dependencies | 1106 | 955 | 0.8635 | 0.8635 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Annual Target | 1106 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Design | 1106 | 1241 | 1.1221 | 1.1221 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Rebaseline | 0 | 1106 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Total in WP | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Execute | 2 | 3 | 1.5 | 1.5 | TRUE
ED Projects | Sandra Cullings | ED Cable | EOY Forecast | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Annual Target | 7 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Schedule | 3 | 7 | 2.3333 | 2.3333 | TRUE
ED Projects | Sandra Cullings | ED Cable | Dependencies | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | Design | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | Rebaseline | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Initiation | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Dependencies | 83 | 77 | 0.9277 | 0.9277 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | EOY Forecast | 0 | 90 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Rebaseline | 0 | 83 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Design | 83 | 85 | 1.0241 | 1.0241 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Initiation | 83 | 90 | 1.0843 | 1.0843 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Schedule | 73 | 80 | 1.0959 | 1.0959 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Total in WP | 0 | 90 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Annual Target | 83 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Execute | 67 | 68 | 1.0149 | 1.0149 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Design | 52 | 68 | 1.3077 | 1.3077 | TRUE
ED Projects | Sandra Cullings | ED Capacity | EOY Forecast | 0 | 73 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Rebaseline | 0 | 52 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Dependencies | 52 | 60 | 1.1538 | 1.1538 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Schedule | 45 | 57 | 1.2667 | 1.2667 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Total in WP | 0 | 73 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Annual Target | 52 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Execute | 34 | 39 | 1.1471 | 1.1471 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Initiation | 52 | 73 | 1.4038 | 1.4038 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Total in WP | 0 | 35 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Dependencies | 33 | 31 | 0.9394 | 0.9394 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Design | 33 | 34 | 1.0303 | 1.0303 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Initiation | 33 | 35 | 1.0606 | 1.0606 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Annual Target | 33 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Schedule | 24 | 32 | 1.3333 | 1.3333 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Execute | 21 | 21 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | EOY Forecast | 0 | 35 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Rebaseline | 0 | 75 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Design | 75 | 90 | 1.2 | 1.2 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Dependencies | 75 | 54 | 0.72 | 0.72 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Schedule | 36 | 52 | 1.4444 | 1.4444 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Annual Target | 75 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Total in WP | 0 | 91 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | EOY Forecast | 0 | 91 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Initiation | 75 | 90 | 1.2 | 1.2 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Execute | 32 | 34 | 1.0625 | 1.0625 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Design | 56 | 58 | 1.0357 | 1.0357 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Dependencies | 56 | 42 | 0.75 | 0.75 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Rebaseline | 0 | 56 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Total in WP | 0 | 59 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Annual Target | 56 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Execute | 35 | 24 | 0.6857 | 0.6857 | TRUE
ED Projects | Sandra Cullings | ED LBOR | EOY Forecast | 0 | 59 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Schedule | 31 | 46 | 1.4839 | 1.4839 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Initiation | 56 | 59 | 1.0536 | 1.0536 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | EOY Forecast | 0 | 10.8564 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Execute | 5 | 6.986 | 1.2725 | 1.3972 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Dependencies | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Initiation | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Total in WP | 0 | 10.8564 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Schedule | 7 | 8.4381 | 1.2089 | 1.2054 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Rebaseline | 0 | 10.86 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Design | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Annual Target | 11 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Annual Target | 15326 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Total in WP | 0 | 21121 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Execute | 12235 | 13344 | 1.0906 | 1.0906 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Rebaseline | 0 | 15326 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Design | 15326 | 19771 | 1.29 | 1.29 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Dependencies | 15326 | 17997 | 1.1743 | 1.1743 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Schedule | 14995 | 17297 | 1.1535 | 1.1535 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | EOY Forecast | 0 | 21121 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Initiation | 15326 | 20614 | 1.345 | 1.345 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Rebaseline | 0 | 146 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Design | 146 | 479 | 3.2808 | 3.2808 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Dependencies | 146 | 353 | 2.4178 | 2.4178 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Schedule | 131 | 229 | 1.7481 | 1.7481 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Annual Target | 146 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | EOY Forecast | 0 | 543 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Execute | 102 | 101 | 0.9902 | 0.9902 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Total in WP | 0 | 543 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Initiation | 146 | 510 | 3.4932 | 3.4932 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Annual Target | 60 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Rebaseline | 0 | 60 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Dependencies | 60 | 54 | 0.9 | 0.9 | TRUE
ED Projects | Sandra Cullings | ED Reliability | EOY Forecast | 0 | 65 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Design | 60 | 63 | 1.05 | 1.05 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Schedule | 36 | 51 | 1.4167 | 1.4167 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Total in WP | 0 | 65 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Execute | 35 | 32 | 0.9143 | 0.9143 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Initiation | 60 | 65 | 1.0833 | 1.0833 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Design | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Schedule | 2 | 2 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Dependencies | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Rebaseline | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Total in WP | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Execute | 2 | 2 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Annual Target | 3 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | EOY Forecast | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Initiation | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Design | 26 | 25 | 0.9615 | 0.9615 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Total in WP | 0 | 25 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | EOY Forecast | 0 | 25 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Rebaseline | 0 | 26 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Annual Target | 26 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Dependencies | 26 | 24 | 0.9231 | 0.9231 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Schedule | 22 | 25 | 1.1364 | 1.1364 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Execute | 19 | 17 | 0.8947 | 0.8947 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Initiation | 26 | 25 | 0.9615 | 0.9615 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Rebaseline | 0 | 193 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Annual Target | 308 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Initiation | 308 | 294 | 0.9545 | 0.9545 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Design | 0 | 100 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Dependencies | 308 | 291 | 0.9448 | 0.9448 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Schedule | 293 | 281 | 0.959 | 0.959 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | EOY Forecast | 0 | 294 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Total in WP | 0 | 294 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Execute | 251 | 289 | 1.1514 | 1.1514 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Rebaseline | 0 | 3000 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Annual Target | 3000 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Design | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | EOY Forecast | 0 | 3426 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Schedule | 2644 | 3147 | 1.1902 | 1.1902 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Dependencies | 3000 | 3290 | 1.0967 | 1.0967 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Total in WP | 0 | 3426 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Execute | 2340 | 2460 | 1.0513 | 1.0513 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Initiation | 3000 | 3426 | 1.142 | 1.142 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Annual Target | 757 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Design | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | EOY Forecast | 0 | 765 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Rebaseline | 0 | 757 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Dependencies | 757 | 761 | 1.0053 | 1.0053 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Schedule | 582 | 710 | 1.2199 | 1.2199 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Total in WP | 0 | 765 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Execute | 384 | 498 | 1.2969 | 1.2969 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Initiation | 757 | 765 | 1.0106 | 1.0106 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | EOY Forecast | 0 | 25918 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Annual Target | 20436 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Dependencies | 20436 | 21617 | 1.0578 | 1.0578 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Schedule | 20506 | 21887 | 1.0673 | 1.0673 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Execute | 16920 | 18736 | 1.1073 | 1.1073 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Rebaseline | 0 | 20436 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Rebaseline | 0 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Design | 20436 | 25018 | 1.2242 | 1.2242 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Total in WP | 0 | 25918 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Initiation | 20436 | 25341 | 1.24 | 1.24 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Execute | 55449 | 46058 | 0.8306 | 0.8306 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Schedule | 52466 | 54896 | 1.0463 | 1.0463 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | EOY Forecast | 0 | 70589 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Total in WP | 0 | 70589 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Rebaseline | 0 | 69150 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Dependencies | 69150 | 59448 | 0.8597 | 0.8597 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Rebaseline | 0 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Design | 69150 | 68818 | 0.9952 | 0.9952 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Annual Target | 69150 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Initiation | 69150 | 68836 | 0.9955 | 0.9955 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Execute | 1311 | 1300 | 0.9916 | 0.9916 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Dependencies | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Total in WP | 0 | 1546 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Schedule | 1314 | 1342 | 1.0213 | 1.0213 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Design | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Annual Target | 1475 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Rebaseline | 0 | 1475 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | EOY Forecast | 0 | 1546 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Initiation | 1475 | 1546 | 1.0481 | 1.0481 | TRUE

## v2
Mega Process | MPO | PDC Program | Phase | Plan | Completions | % to Plan | % to Plan | Check
ED Maintenance | Ron Richardson | COE Capital | Execute | 838 | 971 | 1.1587 | 1.1587 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Design | 1051 | 984 | 0.9363 | 0.9363 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Annual Target | 1051 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Initiation | 1051 | 997 | 0.9486 | 0.9486 | TRUE
ED Maintenance | Ron Richardson | COE Capital | EOY Forecast | 0 | 1034 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Rebaseline | 0 | 1051 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Total in WP | 0 | 1034 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Schedule | 1051 | 943 | 0.8972 | 0.8972 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Dependencies | 1051 | 897 | 0.8535 | 0.8535 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Annual Target | 1106 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | EOY Forecast | 0 | 1243 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Rebaseline | 0 | 1106 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Schedule | 1171 | 1076 | 0.9189 | 0.9189 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Initiation | 1106 | 1241 | 1.1221 | 1.1221 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Design | 1106 | 1241 | 1.1221 | 1.1221 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Total in WP | 0 | 1243 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Dependencies | 1106 | 955 | 0.8635 | 0.8635 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Execute | 884 | 1139 | 1.2885 | 1.2885 | TRUE
ED Projects | Sandra Cullings | ED Cable | Design | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | Annual Target | 7 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Initiation | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | EOY Forecast | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Rebaseline | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Execute | 2 | 3 | 1.5 | 1.5 | TRUE
ED Projects | Sandra Cullings | ED Cable | Total in WP | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Schedule | 3 | 7 | 2.3333 | 2.3333 | TRUE
ED Projects | Sandra Cullings | ED Cable | Dependencies | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Annual Target | 83 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Execute | 67 | 68 | 1.0149 | 1.0149 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Design | 83 | 85 | 1.0241 | 1.0241 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Schedule | 73 | 80 | 1.0959 | 1.0959 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Total in WP | 0 | 90 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Initiation | 83 | 90 | 1.0843 | 1.0843 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | EOY Forecast | 0 | 90 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Rebaseline | 0 | 83 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Dependencies | 83 | 77 | 0.9277 | 0.9277 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Annual Target | 52 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Execute | 34 | 39 | 1.1471 | 1.1471 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Design | 52 | 68 | 1.3077 | 1.3077 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Schedule | 45 | 57 | 1.2667 | 1.2667 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Total in WP | 0 | 73 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Dependencies | 52 | 60 | 1.1538 | 1.1538 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Rebaseline | 0 | 52 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Initiation | 52 | 73 | 1.4038 | 1.4038 | TRUE
ED Projects | Sandra Cullings | ED Capacity | EOY Forecast | 0 | 73 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Schedule | 24 | 32 | 1.3333 | 1.3333 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Design | 33 | 34 | 1.0303 | 1.0303 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Initiation | 33 | 35 | 1.0606 | 1.0606 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | EOY Forecast | 0 | 35 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Execute | 21 | 21 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Total in WP | 0 | 35 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Annual Target | 33 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Dependencies | 33 | 31 | 0.9394 | 0.9394 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Dependencies | 75 | 54 | 0.72 | 0.72 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Rebaseline | 0 | 75 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Total in WP | 0 | 91 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Initiation | 75 | 90 | 1.2 | 1.2 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Design | 75 | 90 | 1.2 | 1.2 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | EOY Forecast | 0 | 91 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Schedule | 36 | 52 | 1.4444 | 1.4444 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Execute | 32 | 34 | 1.0625 | 1.0625 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Annual Target | 75 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Total in WP | 0 | 59 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Schedule | 31 | 46 | 1.4839 | 1.4839 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Rebaseline | 0 | 56 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Initiation | 56 | 59 | 1.0536 | 1.0536 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Execute | 35 | 24 | 0.6857 | 0.6857 | TRUE
ED Projects | Sandra Cullings | ED LBOR | EOY Forecast | 0 | 59 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Annual Target | 56 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Design | 56 | 58 | 1.0357 | 1.0357 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Dependencies | 56 | 42 | 0.75 | 0.75 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Dependencies | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Design | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | EOY Forecast | 0 | 10.8564 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Execute | 5 | 6.986 | 1.2725 | 1.3972 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Annual Target | 11 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Schedule | 7 | 8.4381 | 1.2089 | 1.2054 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Initiation | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Total in WP | 0 | 10.8564 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Rebaseline | 0 | 10.86 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | EOY Forecast | 0 | 21121 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Annual Target | 15326 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Design | 15326 | 19771 | 1.29 | 1.29 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Execute | 12235 | 13344 | 1.0906 | 1.0906 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Initiation | 15326 | 20614 | 1.345 | 1.345 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Rebaseline | 0 | 15326 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Total in WP | 0 | 21121 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Dependencies | 15326 | 17997 | 1.1743 | 1.1743 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Schedule | 14995 | 17297 | 1.1535 | 1.1535 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Design | 146 | 479 | 3.2808 | 3.2808 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Initiation | 146 | 510 | 3.4932 | 3.4932 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Annual Target | 146 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Rebaseline | 0 | 146 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | EOY Forecast | 0 | 543 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Execute | 102 | 101 | 0.9902 | 0.9902 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Schedule | 131 | 229 | 1.7481 | 1.7481 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Total in WP | 0 | 543 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Dependencies | 146 | 353 | 2.4178 | 2.4178 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Initiation | 60 | 65 | 1.0833 | 1.0833 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Schedule | 36 | 51 | 1.4167 | 1.4167 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Rebaseline | 0 | 60 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Total in WP | 0 | 65 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | EOY Forecast | 0 | 65 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Annual Target | 60 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Design | 60 | 63 | 1.05 | 1.05 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Execute | 35 | 32 | 0.9143 | 0.9143 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Dependencies | 60 | 54 | 0.9 | 0.9 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Dependencies | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Rebaseline | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Total in WP | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Design | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Initiation | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Schedule | 2 | 2 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | EOY Forecast | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Execute | 2 | 2 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Annual Target | 3 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Rebaseline | 0 | 26 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Schedule | 22 | 25 | 1.1364 | 1.1364 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | EOY Forecast | 0 | 25 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Execute | 19 | 17 | 0.8947 | 0.8947 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Initiation | 26 | 25 | 0.9615 | 0.9615 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Dependencies | 26 | 24 | 0.9231 | 0.9231 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Design | 26 | 25 | 0.9615 | 0.9615 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Annual Target | 26 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Total in WP | 0 | 25 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | EOY Forecast | 0 | 294 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Initiation | 308 | 294 | 0.9545 | 0.9545 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Execute | 251 | 289 | 1.1514 | 1.1514 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Schedule | 293 | 281 | 0.959 | 0.959 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Dependencies | 308 | 291 | 0.9448 | 0.9448 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Design | 0 | 100 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Rebaseline | 0 | 193 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Total in WP | 0 | 294 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Annual Target | 308 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | EOY Forecast | 0 | 3426 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Initiation | 3000 | 3426 | 1.142 | 1.142 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Execute | 2340 | 2460 | 1.0513 | 1.0513 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Dependencies | 3000 | 3290 | 1.0967 | 1.0967 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Schedule | 2644 | 3147 | 1.1902 | 1.1902 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Design | 0 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Annual Target | 3000 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Rebaseline | 0 | 3000 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Total in WP | 0 | 3426 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | EOY Forecast | 0 | 765 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Execute | 384 | 498 | 1.2969 | 1.2969 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Initiation | 757 | 765 | 1.0106 | 1.0106 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Dependencies | 757 | 761 | 1.0053 | 1.0053 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Schedule | 582 | 710 | 1.2199 | 1.2199 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Rebaseline | 0 | 757 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Design | 0 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Annual Target | 757 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Total in WP | 0 | 765 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Annual Target | 20436 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Initiation | 20436 | 25341 | 1.24 | 1.24 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Rebaseline | 0 | 20436 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Rebaseline | 0 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Design | 20436 | 25018 | 1.2242 | 1.2242 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Schedule | 20506 | 21887 | 1.0673 | 1.0673 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | EOY Forecast | 0 | 25918 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Execute | 16920 | 18736 | 1.1073 | 1.1073 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Total in WP | 0 | 25918 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Dependencies | 20436 | 21617 | 1.0578 | 1.0578 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | EOY Forecast | 0 | 70589 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Rebaseline | 0 | 69150 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Design | 69150 | 68818 | 0.9952 | 0.9952 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Rebaseline | 0 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Total in WP | 0 | 70589 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Schedule | 52466 | 54896 | 1.0463 | 1.0463 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Initiation | 69150 | 68836 | 0.9955 | 0.9955 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Execute | 55449 | 46058 | 0.8306 | 0.8306 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Annual Target | 69150 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Dependencies | 69150 | 59448 | 0.8597 | 0.8597 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Total in WP | 0 | 1546 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Rebaseline | 0 | 1475 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Execute | 1311 | 1300 | 0.9916 | 0.9916 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Design | 0 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Dependencies | 0 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Initiation | 1475 | 1546 | 1.0481 | 1.0481 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Schedule | 1314 | 1342 | 1.0213 | 1.0213 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | EOY Forecast | 0 | 1546 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Annual Target | 1475 | 0 | 0 | 0 | TRUE

## storedProcedure
Mega Process | MPO | PDC Program | Phase | Plan | Completions | % to Plan | % to Plan | Check
ED Maintenance | Ron Richardson | COE Capital | EOY Forecast | 0 | 1034 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Dependencies | 1051 | 897 | 0.8535 | 0.8535 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Annual Target | 1051 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Execute | 838 | 971 | 1.1587 | 1.1587 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Total in WP | 0 | 1034 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Schedule | 1051 | 943 | 0.8972 | 0.8972 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Rebaseline | 0 | 1051 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Design | 1051 | 984 | 0.9363 | 0.9363 | TRUE
ED Maintenance | Ron Richardson | COE Capital | Initiation | 1051 | 997 | 0.9486 | 0.9486 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Total in WP | 0 | 1243 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Rebaseline | 0 | 1106 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Dependencies | 1106 | 955 | 0.8635 | 0.8635 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Annual Target | 1106 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Execute | 884 | 1139 | 1.2885 | 1.2885 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Initiation | 1106 | 1241 | 1.1221 | 1.1221 | TRUE
ED Maintenance | Ron Richardson | COE Expense | EOY Forecast | 0 | 1243 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Schedule | 1171 | 1076 | 0.9189 | 0.9189 | TRUE
ED Maintenance | Ron Richardson | COE Expense | Design | 1106 | 1241 | 1.1221 | 1.1221 | TRUE
ED Projects | Sandra Cullings | ED Cable | Schedule | 3 | 7 | 2.3333 | 2.3333 | TRUE
ED Projects | Sandra Cullings | ED Cable | Dependencies | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | Execute | 2 | 3 | 1.5 | 1.5 | TRUE
ED Projects | Sandra Cullings | ED Cable | Design | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | Rebaseline | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Initiation | 7 | 7 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Cable | Total in WP | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | Annual Target | 7 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cable | EOY Forecast | 0 | 7 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Schedule | 73 | 80 | 1.0959 | 1.0959 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Initiation | 83 | 90 | 1.0843 | 1.0843 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | EOY Forecast | 0 | 90 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Execute | 67 | 68 | 1.0149 | 1.0149 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Annual Target | 83 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Total in WP | 0 | 90 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Rebaseline | 0 | 83 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Design | 83 | 85 | 1.0241 | 1.0241 | TRUE
ED Projects | Sandra Cullings | ED Cap Cust Voltage Complaints | Dependencies | 83 | 77 | 0.9277 | 0.9277 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Initiation | 52 | 73 | 1.4038 | 1.4038 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Schedule | 45 | 57 | 1.2667 | 1.2667 | TRUE
ED Projects | Sandra Cullings | ED Capacity | EOY Forecast | 0 | 73 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Annual Target | 52 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Design | 52 | 68 | 1.3077 | 1.3077 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Execute | 34 | 39 | 1.1471 | 1.1471 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Rebaseline | 0 | 52 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Total in WP | 0 | 73 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Capacity | Dependencies | 52 | 60 | 1.1538 | 1.1538 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Schedule | 24 | 32 | 1.3333 | 1.3333 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Annual Target | 33 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Dependencies | 33 | 31 | 0.9394 | 0.9394 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Initiation | 33 | 35 | 1.0606 | 1.0606 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Design | 33 | 34 | 1.0303 | 1.0303 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Execute | 21 | 21 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | Total in WP | 0 | 35 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Dist Protec Device/MSO Replace | EOY Forecast | 0 | 35 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Execute | 32 | 34 | 1.0625 | 1.0625 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Initiation | 75 | 90 | 1.2 | 1.2 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Schedule | 36 | 52 | 1.4444 | 1.4444 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | EOY Forecast | 0 | 91 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Annual Target | 75 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Total in WP | 0 | 91 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Rebaseline | 0 | 75 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Design | 75 | 90 | 1.2 | 1.2 | TRUE
ED Projects | Sandra Cullings | ED Fusesaver | Dependencies | 75 | 54 | 0.72 | 0.72 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Schedule | 31 | 46 | 1.4839 | 1.4839 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Execute | 35 | 24 | 0.6857 | 0.6857 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Rebaseline | 0 | 56 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Design | 56 | 58 | 1.0357 | 1.0357 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Initiation | 56 | 59 | 1.0536 | 1.0536 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Total in WP | 0 | 59 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Annual Target | 56 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | EOY Forecast | 0 | 59 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED LBOR | Dependencies | 56 | 42 | 0.75 | 0.75 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Annual Target | 11 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Execute | 5 | 6.986 | 1.2725 | 1.3972 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | EOY Forecast | 0 | 10.8564 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Total in WP | 0 | 10.8564 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Initiation | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Dependencies | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Rebaseline | 0 | 10.86 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Design | 11 | 10.8564 | 0.9997 | 0.9869 | FALSE
ED Projects | Sandra Cullings | ED OH Conductor Repl Non-HFTD | Schedule | 7 | 8.4381 | 1.2089 | 1.2054 | FALSE
ED Projects | Sandra Cullings | ED Pole Repl | Execute | 12235 | 13344 | 1.0906 | 1.0906 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | EOY Forecast | 0 | 21121 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Dependencies | 15326 | 17997 | 1.1743 | 1.1743 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Total in WP | 0 | 21121 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Schedule | 14995 | 17297 | 1.1535 | 1.1535 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Initiation | 15326 | 20614 | 1.345 | 1.345 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Rebaseline | 0 | 15326 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Annual Target | 15326 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Pole Repl | Design | 15326 | 19771 | 1.29 | 1.29 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Design | 146 | 479 | 3.2808 | 3.2808 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Execute | 102 | 101 | 0.9902 | 0.9902 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Dependencies | 146 | 353 | 2.4178 | 2.4178 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Initiation | 146 | 510 | 3.4932 | 3.4932 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Schedule | 131 | 229 | 1.7481 | 1.7481 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Rebaseline | 0 | 146 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Annual Target | 146 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | Total in WP | 0 | 543 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Proactive Transformer Repl | EOY Forecast | 0 | 543 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Schedule | 36 | 51 | 1.4167 | 1.4167 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Annual Target | 60 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Rebaseline | 0 | 60 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Initiation | 60 | 65 | 1.0833 | 1.0833 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Dependencies | 60 | 54 | 0.9 | 0.9 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Total in WP | 0 | 65 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Design | 60 | 63 | 1.05 | 1.05 | TRUE
ED Projects | Sandra Cullings | ED Reliability | EOY Forecast | 0 | 65 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Reliability | Execute | 35 | 32 | 0.9143 | 0.9143 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Rebaseline | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Schedule | 2 | 2 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Annual Target | 3 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | EOY Forecast | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Initiation | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Total in WP | 0 | 3 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Execute | 2 | 2 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Design | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED Rule 20A | Dependencies | 3 | 3 | 1 | 1 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Schedule | 22 | 25 | 1.1364 | 1.1364 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Annual Target | 26 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Rebaseline | 0 | 26 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | EOY Forecast | 0 | 25 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Initiation | 26 | 25 | 0.9615 | 0.9615 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Total in WP | 0 | 25 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Execute | 19 | 17 | 0.8947 | 0.8947 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Design | 26 | 25 | 0.9615 | 0.9615 | TRUE
ED Projects | Sandra Cullings | ED WFM Dist Line MSO Replace | Dependencies | 26 | 24 | 0.9231 | 0.9231 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Total in WP | 0 | 294 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Schedule | 293 | 281 | 0.959 | 0.959 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Rebaseline | 0 | 193 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Initiation | 308 | 294 | 0.9545 | 0.9545 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Dependencies | 308 | 291 | 0.9448 | 0.9448 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Design | 0 | 100 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Annual Target | 308 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | EOY Forecast | 0 | 294 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Line Sensors | Execute | 251 | 289 | 1.1514 | 1.1514 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Annual Target | 3000 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Total in WP | 0 | 3426 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Initiation | 3000 | 3426 | 1.142 | 1.142 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Design | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | EOY Forecast | 0 | 3426 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Rebaseline | 0 | 3000 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Execute | 2340 | 2460 | 1.0513 | 1.0513 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Dependencies | 3000 | 3290 | 1.0967 | 1.0967 | TRUE
ED Projects | Sandra Cullings | ED WFM Non-Exempt Expulsion Fuses HFTD | Schedule | 2644 | 3147 | 1.1902 | 1.1902 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Design | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Execute | 384 | 498 | 1.2969 | 1.2969 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Total in WP | 0 | 765 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | EOY Forecast | 0 | 765 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Annual Target | 757 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Dependencies | 757 | 761 | 1.0053 | 1.0053 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Schedule | 582 | 710 | 1.2199 | 1.2199 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Rebaseline | 0 | 757 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | ED WFM Surge Arresters HFTD | Initiation | 757 | 765 | 1.0106 | 1.0106 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Rebaseline | 0 | 20436 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Schedule | 20506 | 21887 | 1.0673 | 1.0673 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Rebaseline | 0 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Annual Target | 20436 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | EOY Forecast | 0 | 25918 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Total in WP | 0 | 25918 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Initiation | 20436 | 25341 | 1.24 | 1.24 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Dependencies | 20436 | 21617 | 1.0578 | 1.0578 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Design | 20436 | 25018 | 1.2242 | 1.2242 | TRUE
ED Maintenance | Ron Richardson | Maintenance Capital | Execute | 16920 | 18736 | 1.1073 | 1.1073 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Initiation | 69150 | 68836 | 0.9955 | 0.9955 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Schedule | 52466 | 54896 | 1.0463 | 1.0463 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Design | 69150 | 68818 | 0.9952 | 0.9952 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Dependencies | 69150 | 59448 | 0.8597 | 0.8597 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Total in WP | 0 | 70589 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Rebaseline | 0 | 69150 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Rebaseline | 0 | 0 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Execute | 55449 | 46058 | 0.8306 | 0.8306 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | EOY Forecast | 0 | 70589 | 0 | 0 | TRUE
ED Maintenance | Ron Richardson | Maintenance Expense | Annual Target | 69150 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Annual Target | 1475 | 0 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Schedule | 1314 | 1342 | 1.0213 | 1.0213 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Total in WP | 0 | 1546 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Initiation | 1475 | 1546 | 1.0481 | 1.0481 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Rebaseline | 0 | 1475 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Dependencies | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Design | 0 | 0 | 1 | 0 | FALSE
ED Projects | Sandra Cullings | Mobile Home Park Electric | EOY Forecast | 0 | 1546 | 0 | 0 | TRUE
ED Projects | Sandra Cullings | Mobile Home Park Electric | Execute | 1311 | 1300 | 0.9916 | 0.9916 | TRUE